Project specification report – network biology research labs

spring 2026

This report should be submitted only after the supervisor(s) approval

Project name: Representation Learning of Cell-Line data for Drug Synergy

Supervisor’s name: Ronen Taub Johnatan Savir

Student’s name: Arnold Cheskis

Main goals of the project: The project studies drug synergy prediction on the DrugComb dataset, with the main research goal of improving the cell-line / gene-expression encoder used in the model. A controlled DeepSynergy-style baseline was built first, then evaluated under several split strategies to test whether gene-expression information improves performance. The next step is to replace simple high-dimensional input with better compressed or biologically informed cell-line representations. The project goal is to build a supervised pipeline that uncover the interplay between genes and drugs in high drug synergy prediction regime.

Future Tasks breakdown (try to make is as detailed as possible) Past – present (26.4): Complete baseline model based on the DeepSynergy paper, the remaining 10 fold cross-validation experiments with proper drug and celline exclusions, to generalize model, and add regression predictions and training plots. Compress raw celline data from ~24k deminsions to 128. Encode the smiles molecular representations of the drugs to embeddings. 1. 26.4.26 – 1.5: Add SOA to baseline and detect local and global triggers. Replace existing PCA128 with GNN, LLM or other architecture we can reverse engineer to the gene level. Use the same architecture to encode the molecules’ SMILES representation. Achieve at least the same performance as the baseline model. 2. 1.5 – 5.5: Perform reverse-engineering / attribution analysis on the trained models to identify which genes or compressed components influence predictions most strongly. Repeat for molecules’ encoding model. 3. 6.5 – 17.5: Investigate whether what influences performance and how it can be improved for both a 2-drug synergy prediction and for 1 drug. 4. 18.5 +: Compare improved compression to SOTA models (see papers). Potentially apply the implemented compression to their models. 5. If the simpler compression baselines are promising, move toward biologically informed encoders that can incorporate pathway or interaction-network structure. 10. Summarize the findings into a clear recommendation for which cell-line representation is the best starting point for the next stage of the research/paper.

Relevant papers in the project: 1. Preuer, K., Lewis, R. P. I., Hochreiter, S., Bender, A., Bulusu, K. C., and Klambauer, G. DeepSynergy: predicting anti-cancer drug synergy with Deep Learning. This paper is the main conceptual baseline for the current MLP-based synergy predictor. 2. Kuru, H. I., Tastan, O., and Cicek, A. E. MatchMaker: A Deep Learning Framework for Drug Synergy Prediction. This is the main reference implementation used to understand a stronger drug-synergy pipeline and where gene expression enters the model. 3. Zagidullin, B. et al. DrugComb: an integrative cancer drug combination data portal. This paper is directly relevant because DrugComb is the main data source used throughout the project. 4. AuDNNsynergy. This line of work is relevant as a baseline for autoencoder-style compression of high-dimensional omics features before synergy prediction. 5. PRODeepSyn and TranSynergy. These are relevant next-stage references because they motivate network-informed or biologically structured encoders for gene-expression data. 6. TBD

Working Environment (software/hardware..) IDE - VScode AI tools – Codex Code - Python 3.10+ workspace using `uv`, with `pandas`, `numpy`, `matplotlib`, `PyTDC`, `torch`, `scikit-learn, and other libraries/packages. Hardware - GPU support is useful for longer experiments but not required for all stages. Database – TDC DrugComb

Specific needs from the lab engineer Not specified.